## Project Status
Team #: | 1
Project Name: | Snapify
Date of Submission: | 02/14/2024
Release Plan # | Sprint Plan # | Expected Completion Date | Actual Completion Date | Status | Comments / Reasons | Resolved Issues
Release 1 | Sprint 1 | 2024-07-02 | 2024-07-02 | Completed |  | N/A
Release 1 | Sprint 2 | 2/14/2024 |  | Not Started |  | N/A
Release 1 | Sprint 3 | 2/21/2024 |  | Not Started |  | N/A
Release 2 | Sprint 1 | 2024-06-03 |  | Not Started |  | N/A
Release 2 | Sprint 2 | 3/13/2024 |  | Not Started |  | N/A
Release 2 | Sprint 3 | 3/20/2024 |  | Not Started |  | N/A
Release 3 | Sprint 1 | 3/27/2024 |  | Not Started |  | N/A
Release 3 | Sprint 2 | 2024-03-04 |  | Not Started |  | N/A
Release 3 | Sprint 3 | 2024-10-04 |  | Not Started |  | N/A
Final Project Release and Presentation |  | 4/17/2024 |  | Not Started |  | N/A