## Release Plan
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Release Plan (backlog)
| Release # | 1
| Release Date: | 2024-02-21
| Team: | 1
| Project: | Snapify
Bitbucket Link: https://bitbucket.org/mapd726/workspace/overview/
Story ID | Sprint | Story Title | Story Points | Status
1 | 1 | As user I can see splash screen before redirecting to the login page to see the application logo with name | 1 | Completed
2 | 1 | As user I can register into the application to login into the application | 1 | Completed
3 | 1 | As user I can login into the application to see the homepage of the application | 1 | Completed
4 | 1 | As user I can logout from the application to go bac to the login page | 1 | Completed
5 | 1 | As admin I can see splash screen before redirecting to the login page to see the application logo with name to see application logo with name | 1 | Completed
6 | 1 | As user I can search for product by other attributes | 1 | Completed
7 | 1 | As admin I can login into the application see the dashboard of the admin panel in the application | 1 | Completed
8 | 1 | As admin I can logout from the application to go back to the login page | 1 | Completed
Story ID | Sprint | Story Title | Story Points | Status
9 | 2 | As user I can access a personalized home screen upon logging in to easily navigate and find relevant information and options | 5 | Completed
10 | 2 | As admin I can have a comprehensive dashboard upon login to efficiently manage products, orders, and user data | 3 | Completed
11 | 2 | As user I can be able to edit my profile information to keep my details up-to-date and accurate | 3 | Completed
12 | 2 | As admin I can modify my profile settings to keep my details up-to-date and accurate | 3 | Completed
Story ID | Sprint | Story Title | Story Points | Status
13 | 3 | As a user I can see all products based on selected category to easily browse and find items of interest | 5 | Completed
14 | 3 | As a user I can see product details page of selected product to know more about the product | 5 | Completed