## Sprint 1
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 1
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
1 | 1 | As user I can see splash screen before redirecting to the login page to see the application logo with name | A customer or individual who wants to access the application and use its features. | The splash screen displays the application logo and name. After a few seconds, the user is automatically redirected to the login page. | Design and implement splash screen component. Integrate logo and application name into the splash screen. Implement redirection to the login page after a set duration. | Kajal, Khanjan | 0.5 | Done
2 | 1 | As user I can register into the application so I can login into the application | A new user who wants to create an account on the application to access personalized features and functionalities. | The registration form includes fields for username, email, and password. Upon successful registration, the user receives a confirmation message. | Design and implement registration form UI. Implement backend logic for user registration. Handle registration success and failure scenarios. | Kajal, Khanjan, Rahul | 3 | Done
3 | 1 | As user I can login into the application to see the homepage of the application | A registered user who wants to log in to the application to access the main interface and explore its features. | The login page includes fields for username/email and password. Upon successful login, the user is redirected to the homepage. | Design and implement login form UI. Implement backend logic for user authentication. Handle login success and failure scenarios. | Kajal, Khanjan, Rahul | 2 | Done
4 | 1 | As user I can logout from the application to go back to the login page | A logged-in user who wants to securely log out from the application to end the current session. | The user can access the logout option from the navigation menu. Upon logout, the user is redirected to the login page. | Implement logout functionality. Ensure proper session handling and redirection to the login page. | Khanjan | 0.5 | Done
5 | 1 | As admin I can see splash screen before redirecting to the login page to see the application logo with name | An authorized administrator or staff member who manages the application's backend and performs administrative tasks. | The splash screen displays the application logo and name. After a few seconds, the admin is automatically redirected to the login page. | Design and implement splash screen component. Integrate logo and application name into the splash screen. Implement redirection to the login page after a set duration. | Kajal, Khanjan | 0.5 | Done
6 | 1 | As admin I can login into the application see the dashboard of the admin panel in the application | An authorized administrator or staff member who wants to log in to the application's admin panel to access backend management tools. | The login page includes fields for admin username/email and password. Upon successful login, the admin is redirected to the admin dashboard. | Design and implement admin login form UI. Implement backend logic for admin authentication. Handle login success and failure scenarios. | Kajal, Khanjan, Rahul | 2 | Done
7 | 1 | As admin I can logout from the application to go back to the login page | An authorized administrator or staff member who wants to securely log out from the admin panel to end the current session. | The admin can access the logout option from the admin dashboard. Upon logout, the admin is redirected to the login page. | Implement logout functionality for admin users. Ensure proper session handling and redirection to the login page. | Khanjan | 0.5 | Done

## Sprint 2
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 2
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
1 | 5 | As user I can access a personalized home screen upon logging in to easily navigate and find relevant information and options | A logged-in user who wants to access a personalized home screen upon logging in to easily navigate and find relevant information and options. | Upon login, the user is directed to a home screen displaying personalized content, such as recommended products, recent orders, and account information. | Design and implement personalized home screen UI. Integrate backend API to fetch user-specific data for the home screen. Test home screen functionality with various user accounts. | Kajal, Khanjan, Bhargav | 6 | Done
2 | 5 | As admin I can have a comprehensive dashboard upon login to efficiently manage products, orders, and user data | An authorized administrator or staff member who wants to access a comprehensive dashboard upon logging in to efficiently manage products, orders, and user data. | Upon login, the admin is directed to a dashboard displaying key metrics, product management tools, order management features, and user data management options. | Design and implement admin dashboard UI. Integrate backend API to fetch and update data for the admin dashboard. Test dashboard functionality with various admin accounts. | Khanjan, Bhargav | 4 | Done
3 | 3 | As user I can be able to edit my profile information to keep my details up-to-date and accurate | A registered user who wants to edit their profile information, such as name, email, or password, to keep their details up-to-date and accurate. | The user can access the profile editing option from the user settings menu. The profile editing form allows users to modify their personal information such as name, email, and password. Upon saving changes, the user receives a confirmation message. | Design and implement profile editing UI. Implement backend logic for profile information update. Handle profile update success and failure scenarios. | Kajal, Khanjan, Rahul | 3 | Done
4 | 3 | As admin I can modify my profile settings to keep my details up-to-date and accurate | An authorized administrator or staff member who wants to modify their profile settings, such as name, email, or password, to keep their details up-to-date and accurate. | The admin can access the profile editing option from the admin settings menu. The profile editing form allows admins to modify their personal information such as name, email, and password. Upon saving changes, the admin receives a confirmation message. | Design and implement admin profile editing UI. Implement backend logic for admin profile information update. Handle profile update success and failure scenarios. | Kajal, Khanjan, Rahul | 3 | Done

## Sprint 3
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 3
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
1 | 5 | As a user I can see all products based on selected category to easily browse and find items of interest | A user wants to see all products based on a selected category to easily browse and find items of interest. | Upon selecting a category, the user should be presented with a list of products belonging to that category. | Implement backend logic to fetch products based on selected category. Test product listing functionality with various category selections | Khanjan, Rahul, Bhargav, Kajal | 6 | Done
2 | 5 | As a user I can see product details page of selected product to know more about the product | A user wants to see the product details page of a selected product to know more about the product. | When clicking on a product, the user should be directed to a product details page displaying information such as description, price, and images. | Design product details UI. Implement backend logic to fetch product details. Test product details functionality with various product selections. | Khanjan, Bhargav, Kajal | 4 | Done