## Sprint 1
Team #: 1
Project Name: | Snapify
Date of Submission: 07/02/2024
Sprint 1
Test Case Id | Test Case Description | Test steps | Test Data | Expected Result | Actual Result | Pass / Fail | Tester Name(s) | Date
T001 | Check splash screen display for users | Launch the application. | N/A | Splash screen displays the application logo and name. | Splash screen displays the application logo and name. | Pass | Kajal | 2024-02-05
T002 | Register into the application | Enter valid informations (e.g. name, email, password) | Valid registration details (e.g., name, email, password) | User is successfully registered and redirected. | User is successfully registered and redirected. | Pass | Kajal | 2024-02-05
T003 | User login to the application | Enter invalid informations (username and password) | Invalid login credentials (username and password) | User is not able to login as invalid credentials are entered | User able to login to the application | Fail | Kajal | 2024-02-05
T003 | User login to the application | Enter valid informations (username and password) | valid login credentials (username and password) | User is successfully logged in and directed. | User will be redirected to homescreen | Pass | Kajal | 2024-02-06
T004 | User logout from the application | Navigate to the "Login" option in the application. | Click on the logout button. | User is successfully logged out and redirected to login screen. | User will be redirected to login screen | Pass | Kajal | 2024-02-06
T005 | Check splash screen display for admin | Launch the application. | N/A | Splash screen displays the application logo and name. | Splash screen displays the application logo and name. | Pass | Kajal | 2024-02-06
T006 | Admin login to the application | Enter valid informations (username and password) | Valid admin login credentials (username and password) | Admin is successfully logged in and directed. | Admin is successfully logged in and directed. | Pass | Kajal | 2024-02-07
T007 | Admin logout from the application | Navigate to the "Login" option in the application. | Click on the logout button | Admin is successfully logged out and redirected to login screen. | Admin will be redirected to login screen | Pass | Kajal | 2024-02-07

## Sprint 2
Team #: 1
Project Name: | Snapify
Date of Submission: 02/14/2024
Sprint 2
Test Case Id | Test Case Description | Test steps | Test Data | Expected Result | Actual Result | Pass / Fail | Tester Name(s) | Date
TC008 | Verify user is directed to personalized home screen upon login | 1. Open the application and login with user credentials. 2. Observe the screen displayed after successful login. | User credentials for login. | User is directed to a home screen displaying personalized content: recommended products, recent orders, and account information. | User is directed to a home screen displaying personalized content: recommended products, recent orders, and account information. | Pass | Kajal | 02/14/2024
TC009 | Verify admin is directed to comprehensive dashboard upon login | 1. Open the application and login with admin credentials. 2. Observe the screen displayed after successful login. | Admin credentials for login. | Admin is directed to a dashboard displaying key metrics, product management tools, order management features, and user data management options. | Admin is directed to a dashboard displaying key metrics, product management tools, order management features, and user data management options. | Pass | Kajal | 02/14/2024
TC010 | User not able to edit profile information | 1. Login to the application as a registered user. 2. Navigate to the profile. 3. Modify the profile information with wrong input for any field (e.g., name, email, password). 4. Save the changes. 5. Validation message error. | Modified user profile information with invalid input. | User's profile information is successfully updated, and a confirmation message is displayed. | User's profile not updated as input information was not valid. Validation error message displayed. | Fail | Kajal | 02/14/2024
TC010 | User can edit profile information successfully | 1. Login to the application as a registered user. 2. Navigate to the user settings menu and select the option to edit profile. 3. Modify the profile information (e.g., name, email, password). 4. Save the changes. 5. Check for confirmation message. | Modified user profile information. | User's profile information is successfully updated, and a confirmation message is displayed. | User's profile information is successfully updated, and a confirmation message is displayed. | Pass | Kajal | 02/14/2024
TC011 | Admin not able to edit profile information | 1. Login to the application as an admin. 2. Navigate to the profile. 3. Modify the profile settings with wrong input for any field (e.g., name, email, password). 4. Save the changes. 5. Check for confirmation message. | Modified admin profile information with invalid input. | Admin's profile settings are successfully updated, and a confirmation message is displayed. | Admin's profile not updated as input information was not valid. Validation error message displayed. | Fail | Kajal | 02/14/2024
TC012 | Admin can modify profile settings successfully | 1. Login to the application as an admin. 2. Navigate to the admin settings menu and select the option to edit profile. 3. Modify the profile settings (e.g., name, email, password). 4. Save the changes. 5. Check for confirmation message. | Modified admin profile settings. | Admin's profile settings are successfully updated, and a confirmation message is displayed. | Admin's profile settings are successfully updated, and a confirmation message is displayed. | Pass | Kajal | 02/14/2024

## Sprint 3
Team #: 1
Project Name: | Snapify
Date of Submission: 02/21/2024
Sprint 3
Test Case Id | Test Case Description | Test steps | Test Data | Expected Result | Actual Result | Pass / Fail | Tester Name(s) | Date
TC013 | Check product listing functionality with selected category | 1. Open the application. | Selected category | User is presented with a list of products in the category. | User is presented with a list of products in the category. | Pass | Kajal | 02/21/2024
TC014 | Check product details page display upon selecting a product | 1. Open the application. | Selected product | User is directed to the product details page. | User is directed to the product details page. | Pass | Kajal | 02/21/2024
TC015 | Check product details information accuracy | 1. Open the product details page. | Product details | Product details match the database. | Product details match the database. | Pass | Kajal | 02/21/2024