## Sprint 1
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 1
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
1 | 2 | As admin I can add product information (design) | An admin wants to add product information to maintain an updated inventory. | The admin should be able to fill in product details and submit them. | Design product addition form UI. | Kajal, Khanjan | 2 | Done
2 | 1 | As admin I can delete product information (design) | An admin wants to delete product information to manage product listings efficiently. | The admin should be able to select products for deletion and confirm the action. | Design product deletion functionality UI. | Kajal, Khanjan | 1 | Done
3 | 2 | As admin I can update product information (design) | An admin wants to update product information to ensure accurate product details. | The admin should be able to edit product details and save changes. | Design product update form UI. | Kajal, Khanjan | 2 | Done
4 | 1 | As admin I can view product information (design) | An admin wants to view product information to have access to product details. | The admin should be able to navigate through product listings and view detailed information for each product. | Design product details viewing UI. | Kajal, Khanjan | 1 | Done
5 | 2 | As user I can add products in cart (design) | A user wants to add products to the cart for selection before purchase. | The user should be able to browse products and add selected items to the cart. | Design cart functionality UI. | Kajal, Khanjan | 2 | Done
6 | 2 | As user I can view products in cart (design) | A user wants to view selected items in the cart before checkout. | The user should be able to access the cart and view all selected items along with their details. | Design cart viewing UI. | Kajal, Khanjan | 2 | Done
7 | 1 | As user I can delete products in cart (design) | A user wants to delete selected items from the cart. | The user should be able to remove items from the cart with ease. | Design cart deletion UI. | Kajal, Khanjan | 1 | Done

## Sprint 2
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 2
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
8 | 2 | As admin I can add product information (development) | An admin wants to add product information to maintain an updated inventory. | The admin should be able to fill in product details and submit them. | Develop product addition functionality. | Kajal, Khanjan | 3 | Done
9 | 1 | As admin I can delete product information (development) | An admin wants to delete product information to manage product listings efficiently. | The admin should be able to select products for deletion and confirm the action. | Develop product deletion functionality. | Rahul, Khanjan | 1 | Done
10 | 2 | As admin I can update product information (development) | An admin wants to update product information to ensure accurate product details. | The admin should be able to edit product details and save changes. | Develop product update functionality. | Khanjan, Bhargav | 3 | Done
11 | 1 | As admin I can view product information (development) | An admin wants to view product information to have access to product details. | The admin should be able to navigate through product listings and view detailed information for each product. | Develop product details viewing functionality. | Khanjan | 1 | Done
12 | 2 | As user I can add products in cart (development) | A user wants to add products to the cart for selection before purchase. | The user should be able to browse products and add selected items to the cart. | Develop cart functionality. | Bhargav, Khanjan | 2 | Done
13 | 2 | As user I can view products in cart (development) | A user wants to view selected items in the cart before checkout. | The user should be able to access the cart and view all selected items along with their details. | Develop cart viewing functionality. | Rahul, Khanjan | 2 | Done
14 | 1 | As user I can delete products in cart (development) | A user wants to delete selected items from the cart. | The user should be able to remove items from the cart with ease. | Develop cart deletion functionality. | Rahul, Khanjan | 1 | Done

## Sprint 3
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 2
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
15 | 2 | As admin I can create an order processing screen to manage order status. | An admin needs the ability to create an order processing screen to efficiently manage the status of orders. | 1. The order processing screen allows admins to view and update the status of orders. 2. Admins can update the status of orders to reflect changes in the order processing workflow. | 1. Design and develop the order processing screen UI. 2. Implement backend logic to fetch and update order status information. 3. Test order processing screen functionality with various order scenarios. | Kajal, Khanjan | 3 | Done
16 | 1 | As user I can access current orders status to track the order | Users need the ability to access the current status of their orders for tracking purposes. | 1. Users can view the status of their current orders after logging into their account. 2. The order status includes details such as Product details, status. 3. Users can easily navigate to the order status section from the main dashboard. | 1. Design and implement the order status display UI. 2. Integrate backend APIs to fetch order status information for the logged-in user. 3. Test order status functionality across different user accounts. | Rahul, Khanjan | 1 | Done
17 | 2 | As user I can access previous orders functionality to view my order history. | Users want to access functionality to view their previous orders for reference and tracking purposes. | 1. Users can access a list of their previous orders from their account dashboard. 2. Each previous order entry includes details such as date of purchase, items ordered, and order status. 3. Users can click on a specific order to view more detailed information about that order. | 1. Design and implement the previous orders display UI. 2. Implement backend logic to fetch and display the user's order history. 3. Test previous orders functionality to ensure accurate display of order history and details. | Khanjan, Bhargav | 3 | Done