## Release Plan
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Release Plan (backlog)
| Release # | 2
| Release Date: | 2024-03-20
| Team: | 1
| Project: | Snapify
Bitbucket Link: https://bitbucket.org/mapd726/workspace/overview/
Story ID | Sprint # | Story Title | Hours | Status
1 | 1 | As admin I can add product information (design) to maintain an updated product inventory | 2 | Done
2 | 1 | As admin I can delete the product information (design) to manage product listings effeciently | 1 | Done
3 | 1 | As admin I can update product information (design) to ensure accurate product details | 2 | Done
4 | 1 | As admin I can view product information (design) to have access to product details | 1 | Done
5 | 1 | As a user I can add products in cart (design) to easily select items for purchase | 2 | Done
6 | 1 | As user I can view products in cart (design) to review selected items before checkout | 2 | Done
7 | 1 | As a user I can delete products in cart (design) to manage cart contents easily | 1 | Done
8 | 2 | As admin I can add product information (development) to maintain an updated product inventory | 3 | Done
9 | 2 | As admin I can delete the product information (development) to manage product listings effeciently | 1 | Done
10 | 2 | As admin I can update product information (development) to ensure accurate product details | 3 | Done
11 | 2 | As admin I can view product information (development) to have access to product details | 1 | Done
12 | 2 | As a user I can add products in cart (development) to easily select items for purchase | 2 | Done
13 | 2 | As user I can view products in cart (development) to review selected items before checkout | 2 | Done
14 | 2 | As a user I can delete products in cart (development) to manage cart contents easily | 1 | Done
15 | 3 | As admin I can create an order processing screen to manage order status. | 5 | Done
16 | 3 | As user I can access current orders status to track the order | 3 | Done
17 | 3 | As user I can access previous orders functionality to view my order history. | 3 | Done