## Project Status
Team #: | 1
Project Name: | Snapify
Date of Submission: | 2024-03-13
Release Plan # | Sprint Plan # | Expected Completion Date | Actual Completion Date | Status | Comments / Reasons | Resolved Issues
Release 1 | Sprint 1 | 2024-07-02 | 2024-07-02 | Completed |  | N/A
Release 1 | Sprint 2 | 02/14/2024 | 02/14/2024 | Completed |  | N/A
Release 1 | Sprint 3 | 02/21/2024 | 02/21/2024 | Completed |  | N/A
Release 2 | Sprint 1 | 2024-06-03 | 2024-06-03 | Completed |  | N/A
Release 2 | Sprint 2 | 03/13/2024 | 03/13/2024 | Completed |  | N/A
Release 2 | Sprint 3 | 03/20/2024 | 03/20/2024 | Completed |  | N/A
Release 3 | Sprint 1 | 03/27/2024 | 03/27/2024 | Completed |  | N/A
Release 3 | Sprint 2 | 2024-03-04 |  | Not Started |  | N/A
Release 3 | Sprint 3 | 2024-10-04 |  | Not Started |  | N/A
Final Project Release and Presentation |  | 04/17/2024 |  | Not Started |  | N/A