## Sprint 1
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 1
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
1 | 2 | As user I can see payment gateway to proceed to enter payment details | User wants to see payment gateway to proceed to enter payment details | 1. Upon checkout, a payment gateway option is displayed. 2. Payment gateway interface allows users to enter card details. | 1. Design and integrate payment gateway UI. 2. Implement backend logic to handle payment processing. 3. Test payment gateway functionality | Rahul, Khanjan | 2 | Done
2 | 3 | As user I can enter payment details to proceed to purchase the product | User wants to enter payment details to proceed to purchase the product | 1. On the payment gateway screen, there are fields to enter payment details such as card number, CVV, expiry date, etc. 2. User can enter valid payment details in the provided fields. 3. User can proceed to the next step in the checkout process after entering payment details. | 1. Design and implement payment details entry form UI. 2. Implement validation for entered payment details. 3. Test payment details entry functionality with different input scenarios. | Rahul, Khanjan | 3 | Done
3 | 2 | As user I can make payment to complete my purchase to see all orders | User wants to make payment to complete purchase to see all orders | 1. After entering payment details, the user can click on the "Make Payment" button. 2. Upon successful payment processing, the user receives a confirmation message. 3. User is redirected to the order confirmation page or order summary screen after payment. | 1. Implement functionality to process payment and complete the purchase. 2. Test payment processing functionality with successful transactions. 3. Handle and test scenarios for failed payment transactions. | Rahul, Khanjan | 2 | Done

## Sprint 2
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 2
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
4 | 2 | As admin I can view all user list to manage user accounts efficiently | Admin wants view all user list to manage user accounts efficiently | 1. The admin dashboard includes an option to access the user list. | 1. Design and implement user list UI in the admin dashboard. 2. Implement backend logic to fetch and display user information. 3. Test user list functionality. | Bhargav, Kajal, Khanjan | 2 | Done
5 | 2 | As admin I can edit user details to update user information as needed | Admin wants to edit user details to update user information as needed | 1. The admin dashboard provides an interface to select and edit user details. | 1. Design and implement user details editing UI. 2. Implement backend logic for user details update. 3. Test user details editing functionality. | Rahul, Khanjan, Kajal | 2 | Done
6 | 1 | As admin I can delete user to remove unwanted user accounts | Admin wants to delete user to remove unwanted user accounts | 1. The admin dashboard offers the functionality to select and delete user accounts. | 1. Design and implement user deletion feature in the admin dashboard. 2. Implement backend logic for user deletion. 3. Test user deletion functionality with various scenarios. | Khanjan, Bhargav, Kajal | 1 | Done

## Sheet 3
School of Engineering Technology and Applied Science
ICET Department
Mobile Application Development Project MAPD-726
Team: 1
Project: Snapify
Sprint plan (backlog)
Sprint # 3
Story ID | Story Points | User Story | Story Description | Acceptance Criteria | Tasks | Who is responsible | Hours | Status
7 | 5 | As admin I can generate comprehensive reports including category-wise and product sale reports, along with monthly, and weekly sales analysis to analyze sales performance and make informed business decisions | Admin wants generate comprehensive reports including category-wise and product sale reports, along with monthly, and weekly sales analysis to analyze sales performance and make informed business decisions | 1. The admin dashboard provides an option to generate reports. | 1. Design and implement report generation UI in the admin dashboard. 2. Integrate backend APIs to fetch sales data. 3. Test report generation functionality with various scenarios. | Bhargav, Kajal, Khanjan, Rahul | 5 | Done